## Sheet1
Weekly Capstone Project Status Report – Week 10
Medical Journey Log: A Family Care Tracker
Project Phase: | Implementation Phase (Milestone 4)
Date: | 2025-07-22
Team: | Alex Frear (Solo Developer)
Status: | Task | Team Member | Hours Worked | Hours Remaining
| Completed Child Detail Page with display of related symptoms | Alex Frear | 2 | 0
| Debugged child name population for symptom form | Alex Frear | 1.5 | 0
| Added validation messages and form feedback for symptom entries | Alex Frear | 1.5 | 0
| Final testing and polish for all pages required in Milestone 4 | Alex Frear | 2 | 1
| Began preparing ZIP for submission and verifying rubric items | Alex Frear | 0.5 | 1
Issues/Risks: | Issue or Risk | Owner | Date Reported | Date Resolved
| Risk of scope creep as features are added | Alex Frear | 2025-06-02 | -
| Working solo and balancing project with work/family | Alex Frear | 2025-05-22 | -
| Minor formatting limitations in diagram rendering | Alex Frear | 2025-06-20 | -
| Risk of delay due to dev cert issues on macOS (resolved manually) | Alex Frear | 2025-07-10 | 2025-07-14
| Bug: child name incorrectly appended “Symptom” label | Alex Frear | 2025-07-20 | 2025-07-21
Overall Instructor Feedback/Comments:
I have Integrated Instructor Feedback into Project My Documentation.
☑ Yes | ☐ No
Class Attendance
☑ Online
I met with my Mentor this week.
☐ Yes | ☑ No