## Sheet1
Weekly Capstone Project Status Report – Week 9
Medical Journey Log: A Family Care Tracker
Project Phase: | Implementation Phase (Milestone 4)
Date: | 2025-07-15
Team: | Alex Frear (Solo Developer)
Status: | Task | Team Member | Hours Worked | Hours Remaining
| Researched and implemented many-to-many relationship for caregivers and children | Alex Frear | 2 | 0
| Updated MySQL schema and generated new .sql export | Alex Frear | 1.5 | 0
| Configured new development certificate and verified HTTPS locally | Alex Frear | 2 | 0
| Refactored Program.cs to clean template for Milestone 4 setup | Alex Frear | 1 | 0
| Reviewed backend setup and planned data access layer | Alex Frear | 1 | 2
| Begin coding Razor Pages for child entry and caregiver association | Alex Frear | 0 | 3
| Define data models and repository structure in code | Alex Frear | 0 | 2
| Set up connection string and initial database context in project | Alex Frear | 0 | 1
Issues/Risks: | Issue or Risk | Owner | Date Reported | Date Resolved
| Risk of scope creep as features are added | Alex Frear | 2025-06-02 | -
| Working solo and balancing project with work/family | Alex Frear | 2025-05-22 | -
| Minor formatting limitations in diagram rendering | Alex Frear | 2025-06-20 | -
| Risk of delay due to dev cert issues on macOS (resolved manually) | Alex Frear | 2025-07-10 | 2025-07-14
Overall Instructor Feedback/Comments:
I have Integrated Instructor Feedback into Project My Documentation.
☑ Yes | ☐ No
Class Attendance
☑ Online
I met with my Mentor this week.
☐ Yes | ☑ No