## Sheet1
Weekly Capstone Project Status Report – Week 1
Medical Journey Log: A Family Care Tracker
Project Phase: | Initiation/Planning
Date: | 2025-05-22
Team: | Alex Frear (Solo Developer)
Status: | Task | Team Member | Hours Worked | Hours Remaining
| Reviewed course requirements | Alex Frear | 2 | 0
| Met with professor to clarify expectations | Alex Frear | 0.5 | 0
| Finalized project concept | Alex Frear | 1 | 0
| Drafted Capstone Proposal (in progress) | Alex Frear | 4 | 2
Issues/Risks: | Issue or Risk | Owner | Date Reported | Date Resolved
| Learning macOS development tools | Alex Frear | 2025-05-22 | -
| Balancing time with work/family | Alex Frear | 2025-05-22 | -
Overall Instructor Feedback/Comments:
I have Integrated Instructor Feedback into Project My Documentation.
☑ Yes | ☐ No
Class Attendance
☑ Online
I met with my Mentor this week.
☑ Yes | ☐ No