## Sheet1
Weekly Capstone Project Status Report – Week 4
Medical Journey Log: A Family Care Tracker
Project Phase: | Requirements Design
Date: | 2025-06-11
Team: | Alex Frear (Solo Developer)
Status: | Task | Team Member | Hours Worked | Hours Remaining
| Finalized system requirements document (Milestone 2) | Alex Frear | 4 | 0
| Reviewed and revised user stories for clarity | Alex Frear | 1 | 0
| Mapped functional requirements to UI wireframes | Alex Frear | 2 | 0
| Proofread and prepped submission materials | Alex Frear | 1 | 0
| Planned ahead for Milestone 3 (next phase planning) | Alex Frear | 1 | 0
Issues/Risks: | Issue or Risk | Owner | Date Reported | Date Resolved
| Risk of scope creep as features are added | Alex Frear | 2025-06-02 | -
| Working solo and balancing project with work/family | Alex Frear | 2025-05-22 | -
Overall Instructor Feedback/Comments:
I have Integrated Instructor Feedback into Project My Documentation.
☑ Yes | ☐ No
Class Attendance
☑ Online
I met with my Mentor this week.
☐ Yes | ☑ No