## Sheet1
Weekly Capstone Project Status Report – Week 8
Medical Journey Log: A Family Care Tracker
Project Phase: | Requirements Design
Date: | 2025-07-08
Team: | Alex Frear (Solo Developer)
Status: | Task | Team Member | Hours Worked | Hours Remaining
| Completed final review of UI Screen Specifications section | Alex Frear | 2 | 0
| Finalized Hardware & Configuration Notes | Alex Frear | 2 | 0
| Completed proofreading and made final edits to Milestone 3 document | Alex Frear | 2 | 0
| Submitted Milestone 3 Final Architectural Plan | Alex Frear | 1 | 0
| Reviewed Milestone 4 requirements and planned initial implementation tasks | Alex Frear | 1 | 2
| Began setting up local development environment for Milestone 4 implementation | Alex Frear | 1 | 3
Issues/Risks: | Issue or Risk | Owner | Date Reported | Date Resolved
| Risk of scope creep as features are added | Alex Frear | 2025-06-02 | -
| Working solo and balancing project with work/family | Alex Frear | 2025-05-22 | -
| Minor formatting limitations in diagram rendering | Alex Frear | 2025-06-20 | -
Overall Instructor Feedback/Comments:
I have Integrated Instructor Feedback into Project My Documentation.
☑ Yes | ☐ No
Class Attendance
☑ Online
I met with my Mentor this week.
☐ Yes | ☑ No